PROJECT CHARTER
Online Clothing Store Launch

| Project Name | StyleNest – Online Clothing Store Launch |
| --- | --- |
| Project Sponsor | Chief Executive Officer |
| Project Manager | Head of E-Commerce |
| Date Prepared | April 18, 2026 |
| Target Launch Date | October 31, 2026 |
| Version | 1.0 – Initial Charter |

# 1. Project Purpose & Background

StyleNest is a direct-to-consumer online clothing store targeting fashion-forward millennials and Gen Z shoppers aged 18–35. The brand will offer curated seasonal collections across men's and women's categories, delivered through a best-in-class digital shopping experience. This project charter formally authorises the planning and execution of the full end-to-end launch.

The fashion e-commerce market is growing at an estimated 10.8% CAGR, presenting a compelling commercial opportunity. StyleNest will differentiate through personalised recommendations, sustainable sourcing, and a seamless mobile-first checkout experience.

# 2. Objectives

The project will achieve the following measurable objectives:

- Launch a fully functional e-commerce platform by October 31, 2026 with 500+ SKUs across 10 product categories.

- Acquire 5,000 registered customers within 60 days of launch through targeted digital marketing campaigns.

- Achieve a website performance score of ≥90/100 on Core Web Vitals (PageSpeed, LCP, CLS).

- Process orders end-to-end with ≤48-hour fulfilment time from order placement to dispatch.

- Generate ₹50 Lakhs in gross revenue within the first six months of operation.

- Maintain a Net Promoter Score (NPS) of ≥45 through the first two quarters.

# 3. Scope

## 3.1 In Scope

- E-commerce website design, development, and deployment (desktop + mobile responsive).

- Product catalogue setup: photography, copywriting, and inventory loading for launch SKUs.

- Payment gateway integration (UPI, credit/debit cards, BNPL options).

- Logistics & last-mile delivery partner integration.

- Customer support portal (live chat, email ticketing, returns management).

- Digital marketing infrastructure: SEO foundation, social media profiles, email marketing setup.

- Warehouse management system (WMS) setup for inventory tracking.

- Staff recruitment and training (operations, customer support, marketing).

## 3.2 Out of Scope

- Physical retail store operations.

- International shipping (Phase 2 initiative).

- Mobile app development (planned for Q1 2027).

- Third-party marketplace listings (Amazon, Flipkart) – deferred to Phase 2.

# 4. Stakeholders

| Stakeholder | Role | Responsibility | Engagement |
| --- | --- | --- | --- |
| CEO / Sponsor | Executive Sponsor | Strategic direction, budget approval | Monthly steering |
| Project Manager | Delivery Lead | Day-to-day execution, reporting | Daily standups |
| Tech Lead / CTO | Technical Authority | Platform architecture & QA | Weekly reviews |
| Marketing Head | Demand Generation | Brand identity, campaigns, SEO | Bi-weekly syncs |
| Operations Manager | Supply Chain | Vendor, logistics, warehouse | Weekly reviews |
| Finance Manager | Budget Control | Budget tracking, payments | Monthly reviews |
| Legal / Compliance | Governance | Contracts, data privacy, GST | As needed |
| Customers (Target) | End Users | Product feedback, purchases | UX research |

# 5. High-Level Timeline

| Phase | Duration | Key Activities | Milestone |
| --- | --- | --- | --- |
| Phase 1 | May – Jun 2026 | Discovery, vendor selection, brand identity | Brand & vendor sign-off |
| Phase 2 | Jun – Aug 2026 | Platform build, catalogue shoot, logistics setup | UAT-ready platform |
| Phase 3 | Aug – Sep 2026 | QA, soft launch (beta), staff training | Beta launch complete |
| Phase 4 | Oct 2026 | Marketing blitz, full public launch | Go-Live Day |
| Phase 5 | Nov – Dec 2026 | Post-launch optimisation, scaling | 30-day review report |

# 6. Budget Summary

| Budget Category | Estimated (₹) | % of Total |
| --- | --- | --- |
| Website Design & Development | 12,00,000 | 24% |
| Inventory (Initial Stock) | 15,00,000 | 30% |
| Marketing & Brand Launch | 10,00,000 | 20% |
| Operations & Logistics Setup | 6,00,000 | 12% |
| Staffing & Training | 4,00,000 | 8% |
| Contingency (10%) | 3,00,000 | 6% |
| TOTAL | 50,00,000 | 100% |

# 7. Assumptions & Constraints

## 7.1 Assumptions

- Budget of ₹50 Lakhs will be approved and available by May 1, 2026.

- All key personnel (PM, Tech Lead, Marketing Head) will be hired by end of May 2026.

- Logistics partner agreements will be finalised within Phase 1.

- Initial inventory supplier contracts will be signed before Phase 2 begins.

## 7.2 Constraints

- Hard launch deadline of October 31, 2026 (pre-festive season imperative).

- Total budget capped at ₹50 Lakhs for Phase 1 delivery.

- Platform must comply with Indian IT Act, Consumer Protection Act, and GST regulations.

# 8. Charter Approval

| Name & Role | Signature | Date |
| --- | --- | --- |
| CEO / Project Sponsor | _____________________ | ____________ |
| Project Manager | _____________________ | ____________ |
| CTO / Tech Lead | _____________________ | ____________ |