PROJECT SCHEDULE
Online Clothing Store – StyleNest Launch Plan
May 2026 – December 2026

# Project Schedule Overview

This schedule covers all tasks required to plan, build, test, and launch the StyleNest online clothing store. Tasks are grouped into five phases spanning May through December 2026. Milestones are highlighted in amber.

| ID | Task | Owner | Start | End | Days | Status |
| --- | --- | --- | --- | --- | --- | --- |
| PHASE 1 — Discovery & Planning ¦ May 1 – Jun 15, 2026 |  |  |  |  |  |  |
| 1.1 | Project kick-off & team onboarding | Project Manager | 01 May | 07 May | 7 days | Planning |
| 1.2 | Business requirements documentation | PM + Marketing | 08 May | 15 May | 8 days | Planning |
| 1.3 | Vendor & technology stack selection | CTO | 08 May | 22 May | 15 days | Planning |
| 1.4 | Brand identity design (logo, palette, tone) | Marketing Head | 15 May | 31 May | 17 days | Planning |
| 1.5 | Legal entity, GST & compliance setup | Legal / Finance | 01 May | 31 May | 31 days | Planning |
| 1.6 | Logistics partner contracts signed | Operations Mgr | 15 May | 15 Jun | 31 days | Planning |
| 1.7 | Supplier / manufacturer agreements | Operations Mgr | 01 May | 15 Jun | 45 days | Planning |
| M1 | ⬦ Brand & Vendor Sign-Off Complete |  |  |  | 0 days | Jun 15, 2026 |
| PHASE 2 — Build & Catalogue ¦ Jun 16 – Aug 31, 2026 |  |  |  |  |  |  |
| 2.1 | E-commerce platform development (front-end) | Dev Team | 16 Jun | 15 Aug | 60 days | Planning |
| 2.2 | Back-end & API integration (payment, WMS) | Dev Team / CTO | 16 Jun | 15 Aug | 60 days | Planning |
| 2.3 | Product photography (500+ SKUs) | Marketing / Ops | 16 Jun | 31 Jul | 46 days | Planning |
| 2.4 | Product copywriting & SEO metadata | Marketing Head | 01 Jul | 15 Aug | 46 days | Planning |
| 2.5 | Inventory upload & catalogue QC | Operations Mgr | 01 Aug | 31 Aug | 31 days | Planning |
| 2.6 | Customer support portal configuration | Ops / CS Lead | 16 Jul | 15 Aug | 31 days | Planning |
| 2.7 | Warehouse setup & WMS configuration | Operations Mgr | 16 Jun | 31 Jul | 46 days | Planning |
| M2 | ⬦ UAT-Ready Platform & Full Catalogue Loaded |  |  |  | 0 days | Aug 31, 2026 |
| PHASE 3 — Testing & Soft Launch ¦ Sep 1 – Sep 30, 2026 |  |  |  |  |  |  |
| 3.1 | System integration & regression testing | Dev Team / QA | 01 Sep | 15 Sep | 15 days | Planning |
| 3.2 | User acceptance testing (UAT) | PM + Key Users | 08 Sep | 20 Sep | 13 days | Planning |
| 3.3 | Performance & load testing | CTO / Dev Team | 15 Sep | 22 Sep | 8 days | Planning |
| 3.4 | Beta / soft launch to 200 invite-only users | PM + Marketing | 22 Sep | 30 Sep | 9 days | Planning |
| 3.5 | Staff training (CS, ops, returns handling) | Ops Manager | 01 Sep | 20 Sep | 20 days | Planning |
| 3.6 | Bug fixes & go-live readiness review | Dev Team / PM | 22 Sep | 30 Sep | 9 days | Planning |
| M3 | ⬦ Beta Launch Complete & Go/No-Go Approved |  |  |  | 0 days | Sep 30, 2026 |
| PHASE 4 — Public Launch ¦ Oct 1 – Oct 31, 2026 |  |  |  |  |  |  |
| 4.1 | Paid digital advertising campaigns live | Marketing Head | 01 Oct | 31 Oct | 31 days | Planning |
| 4.2 | Social media launch content push | Marketing Head | 01 Oct | 31 Oct | 31 days | Planning |
| 4.3 | Influencer & PR outreach | Marketing Head | 01 Oct | 15 Oct | 15 days | Planning |
| 4.4 | Email marketing to waitlist (Day 1 promo) | Marketing Head | 01 Oct | 01 Oct | 1 day | Planning |
| 4.5 | Monitor orders, fulfilment & CS queues | Ops + CS Lead | 01 Oct | 31 Oct | 31 days | Planning |
| M4 | ⬦ Public Go-Live Day |  |  |  | 0 days | Oct 1, 2026 |
| M5 | ⬦ First 1,000 Orders Fulfilled |  |  |  | 0 days | Oct 31, 2026 |
| PHASE 5 — Post-Launch Optimisation ¦ Nov 1 – Dec 31, 2026 |  |  |  |  |  |  |
| 5.1 | Analytics review & conversion optimisation | PM + Marketing | 01 Nov | 30 Nov | 30 days | Planning |
| 5.2 | Customer feedback analysis & product QC | Ops + CS Lead | 01 Nov | 30 Nov | 30 days | Planning |
| 5.3 | Festive season (Diwali) special campaign | Marketing Head | 01 Nov | 15 Nov | 15 days | Planning |
| 5.4 | Operational scaling – additional warehouse staff | Ops Manager | 01 Nov | 15 Nov | 15 days | Planning |
| 5.5 | 30-day post-launch performance report | Project Manager | 01 Nov | 07 Nov | 7 days | Planning |
| 5.6 | Phase 2 roadmap planning (mobile app, intl) | PM + CTO | 01 Dec | 31 Dec | 31 days | Planning |
| M6 | ⬦ 30-Day Review Report Delivered |  |  |  | 0 days | Nov 7, 2026 |
| M7 | ⬦ Phase 2 Roadmap Approved |  |  |  | 0 days | Dec 31, 2026 |

# Milestone Summary

| # | Milestone | Target Date | Phase |
| --- | --- | --- | --- |
| M1 | Brand & Vendor Sign-Off Complete | Jun 15, 2026 | Phase 1 |
| M2 | UAT-Ready Platform & Catalogue Loaded | Aug 31, 2026 | Phase 2 |
| M3 | Beta Launch Complete & Go/No-Go Approved | Sep 30, 2026 | Phase 3 |
| M4 | Public Go-Live Day | Oct 1, 2026 | Phase 4 |
| M5 | First 1,000 Orders Fulfilled | Oct 31, 2026 | Phase 4 |
| M6 | 30-Day Review Report Delivered | Nov 7, 2026 | Phase 5 |
| M7 | Phase 2 Roadmap Approved | Dec 31, 2026 | Phase 5 |