RISK REGISTER & MITIGATION PLAN
Online Clothing Store – StyleNest
Version 1.0  |  April 18, 2026

# Risk Management Approach

This Risk Register identifies potential threats to the successful launch of StyleNest and documents agreed mitigation strategies for each. Risks are assessed on two dimensions — Likelihood (probability of occurrence) and Impact (severity if it occurs) — and assigned a composite Risk Level to prioritise management attention.

| CRITICAL (H×H) | HIGH (H×M or M×H) | MEDIUM (M×M or L×H) | LOW (L×L or L×M) |
| --- | --- | --- | --- |

# Risk Register

| ID | Risk Description | Like. | Impact | Level | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| TECHNOLOGY RISKS |  |  |  |  |  |  |  |
| T-01 | Platform development delays causing missed go-live date | H | H | CRITICAL | Build in 2-week buffer; adopt agile sprints; weekly PM–CTO check-ins; consider phased feature release if needed. | CTO / PM |
| T-02 | Payment gateway integration failures at launch | M | M | HIGH | Integrate and certify with 2 gateways (Razorpay + PayU) for redundancy; conduct load testing pre-launch. | CTO |
| T-03 | Website downtime or performance issues on launch day | M | M | HIGH | Use auto-scaling cloud infrastructure; set up CDN; run load tests simulating 5× expected traffic; have on-call dev team. | CTO |
| T-04 | Data breach or customer data security vulnerability | L | H | MEDIUM | Implement SSL, PCI-DSS compliance, encrypted databases, regular pen-testing; appoint data protection officer. | CTO / Legal |
| T-05 | Third-party API dependencies (logistics, WMS) failing | M | M | MEDIUM | Build API fallback/retry logic; negotiate SLAs with all vendors; test integrations 4 weeks before launch. | CTO / Ops |
| COMMERCIAL & FINANCIAL RISKS |  |  |  |  |  |  |  |
| C-01 | Budget overrun exceeding approved ₹50L ceiling | M | H | HIGH | Monthly budget reviews; enforce change control for scope additions; maintain 10% contingency reserve; weekly finance sign-off. | Finance / PM |
| C-02 | Insufficient customer acquisition – missing 5,000 user target | M | H | HIGH | Launch waitlist 8 weeks pre-go-live; invest in SEO from Day 1; influencer seeding; referral programme at launch. | Marketing |
| C-03 | Pricing uncompetitive vs. established players (Myntra, Ajio) | M | M | MEDIUM | Conduct quarterly competitor pricing audits; differentiate on curation + sustainability rather than price alone. | Marketing / PM |
| C-04 | Low conversion rate on website (below 2%) | M | M | MEDIUM | A/B test landing pages and CTAs during beta; simplify checkout to <4 steps; offer guest checkout; live chat support. | Marketing / CTO |
| C-05 | High product return rate (>25%) impacting margins | M | H | HIGH | Provide accurate size guides + fit videos; enforce supplier QC audits; analyse return reasons weekly and act fast. | Operations |
| SUPPLY CHAIN & OPERATIONS RISKS |  |  |  |  |  |  |  |
| O-01 | Supplier delays causing stockouts at launch | M | H | HIGH | Lock in supplier contracts 3 months early; carry 20% safety stock above forecast; identify 2 backup suppliers per category. | Operations |
| O-02 | Logistics partner unable to meet 48-hr fulfilment SLA | M | H | HIGH | Onboard 2 logistics partners (primary + backup); SLA penalties in contracts; monitor TAT dashboard daily. | Operations |
| O-03 | Warehouse capacity insufficient for festive season surge | L | M | LOW | Book flexible warehouse space with 30% headroom; hire seasonal staff 3 weeks before Diwali peak. | Operations |
| O-04 | Counterfeit / quality inconsistency in products | L | H | MEDIUM | Implement incoming goods QC process; reject-and-return policy; periodic factory audits for key suppliers. | Operations |
| MARKETING & BRAND RISKS |  |  |  |  |  |  |  |
| M-01 | Brand identity fails to resonate with target Gen Z audience | M | H | HIGH | Conduct user research & focus groups in Phase 1; A/B test brand concepts; engage Gen Z social media panel pre-launch. | Marketing |
| M-02 | Negative social media reviews / PR crisis post-launch | L | H | MEDIUM | Establish social listening tools; prepare crisis comms playbook; designate PR spokesperson; 4-hour response SLA. | Marketing / CEO |
| M-03 | Digital advertising CPCs higher than budgeted | M | M | MEDIUM | Diversify acquisition channels (SEO, email, influencers); set ROAS floor on paid campaigns; reallocate budget if needed. | Marketing |
| M-04 | SEO rankings take longer than 3 months to build | H | M | HIGH | Start SEO content 3 months before launch; build backlinks via PR; target long-tail keywords for early wins. | Marketing |
| LEGAL & COMPLIANCE RISKS |  |  |  |  |  |  |  |
| L-01 | GST / tax compliance failures leading to penalties | L | H | MEDIUM | Engage GST consultant from Day 1; automate GST calculation in checkout; schedule quarterly compliance audits. | Finance / Legal |
| L-02 | Data privacy violation (DPDP Act 2023 breach) | L | H | MEDIUM | Appoint Data Protection Officer; publish privacy policy; obtain explicit consent; conduct annual privacy impact assessments. | Legal / CTO |
| L-03 | IP infringement claim on brand name or designs | L | M | LOW | Conduct IP clearance search before brand finalisation; register trademark in Classes 25 & 35 immediately. | Legal |
| PEOPLE & ORGANISATIONAL RISKS |  |  |  |  |  |  |  |
| P-01 | Key hire (Tech Lead / Marketing Head) not joining on time | M | H | HIGH | Begin hiring 2 months before project start; use specialist recruiters; have interim consultants as fallback. | HR / CEO |
| P-02 | Scope creep expanding project beyond original charter | H | M | HIGH | Enforce formal change request process; all scope changes require PM + Sponsor approval; defer non-critical features to Phase 2. | PM / Sponsor |
| P-03 | Key team member departure during critical phase | L | H | MEDIUM | Maintain knowledge documentation for all critical tasks; cross-train team members; competitive retention package. | HR / PM |

# Risk Summary Dashboard

| Risk Level | Count | % of Total | Primary Categories Affected |
| --- | --- | --- | --- |
| CRITICAL | 1 | 4% | Technology (platform delay) |
| HIGH | 12 | 48% | Commercial, Supply Chain, People, Marketing |
| MEDIUM | 9 | 36% | Technology, Legal, Marketing, People |
| LOW | 3 | 12% | Operations, Legal |